## Slide 1: Texas Epidemiology Coordination Project
march 2014-2015 ytd

## Slide 2: Inception
Leadership session was convened 3/3/14 in conjunction with the ELC Epidemiology Conference.
  It was attended by invited epidemiologists from DSHS central and regional offices and local health departments to discuss outbreak investigations in terms of epidemiology skills, capacity issues, and communication across the Texas epidemiology network.
  The workgroup decided on an objective to work on collaboratively in the coming year.
Project Co-chairs –
  LHD-Diana Martinez, PhD, MPH
      RHD-Stacy Davlin, PhD, MPH
          State-Laura Tabony, MPH
          Project Intern –
  Blaine Mallon

## Slide 3: Project Scope
Objective: By February 15, 2015, a work group of central office, regional, and local health department representatives will develop a document that outlines a framework for infectious disease epidemiology and surveillance collaboration across jurisdictions that addresses surge capacity needs.
Goal: A written document that documents best practices for routine surveillance, outbreak investigation, information sharing, lab testing, and surge capacity among the local, regional, and state health departments that comprise the surveillance and epidemiology network in Texas. Issues that need additional exploration, planning, or guidance may also be identified.

## Slide 4: Project Strategy
The workgroup will be headed by Diana Martinez (Harris County Public Health and Environmental Services), Laura Tabony (DSHS Central Office), and Stacy Davlin (Health Service Region 8). Marilyn Felkner, DSHS Manager, Emerging and Acute Disease Branch, will monitor the progress of the project.
Members from the workgroup will include staff that were selected for the leadership session which included representatives from all regional and large local health departments or their replacement delegates. Additional representatives from smaller local health departments will be added.
Four regional meetings will be held for to gather information and ideas. Face-to-face meetings that cut across regions and jurisdictions are important to constructing a robust plan that will be utilized by stakeholders. Locations were selected to draw diverse representatives together.
Conference calls, webinars, and surveys will also be utilized to conduct workgroup business and communicate with all stakeholders.
Intern duties will include analyzing survey information, recording stakeholder input, and drafting plan documents.

## Slide 5: Texas Health Departments

## Slide 6: Face-To-Face Meetings
5/3/14 – Houston
  7/18/14 – Midland
    7/30/14 – San Antonio
      8/13/14 - Dallas
      Attendees from State, 7 RHDs and 32 LHDs

## Slide 7
Houston - 5/3/14
LHD
Beaumont Public Health Department
Bell County Public Health District
City of Houston Health and Human Services Department
Fort Bend County Health Department
Galveston County Health District
Hardin County Health Department
*Harris County Public Health and Environmental Services
Montgomery County Public Health Department
RHD
Region 6/5S
*Region 8
Midland 7/18/14
LHD
Andrews Health Department
City of Amarillo Department of Public Health
City of El Paso Department of Public Health
City of Lubbock Health Department
Ector County Health Department
Plainview-Hale County Health Department
San Angelo Health Department
South Plains Public Health District
Sweetwater-Nolan County Health Department
RHD
Region 1
*Region 8
Region 9/10

## Slide 8: Midland

## Slide 9
San Antonio – 7/30/14
LHD
Austin Travis County Health and Human Services Department
Comal County Health Department
Hays County Health Department
*Harris County Public Health and Environmental Services
Jasper-Newton CO Public Health District
Medina County Health Department
Williamson County and Cities Health District
RHD
*Region 8
Region 11
Region 11 Harlingen
Dallas 8/13/14
LHD
Angelina CO & Cities Health District
Cherokee CO Health Department
Collin CO Health Care Services
Dallas County Health and Human Services
Denton County Health Department
Garland City Health Department
Grayson CO Health Department
*Harris County Public Health and Environmental Services
Northeast Texas Public Health District
Tarrant County Public Health Department
RHD
Region 2/3
Region 7
*Region 8

## Slide 10: Meeting Discussions
Networking
  Common goals
  Collaboration
  Coordination
Similarities and differences
  Structure
  Capacity
  Challenges

## Slide 11: Findings during face-to-face meetings
LHDs have varying sizes and epidemiology capacity
Some LHDs have combined preparedness and epidemiology staff/roles
LHDs have different challenges regarding laboratory capacity
  In general distance and resources are challenges for specimen collection and shipment
Surge capacity
  Some LHDs use resources from within and/or volunteers (i.e. SPH students)
  Administrative resistance to accepting for help from others

## Slide 12: Progress Report/What Now?

## Slide 13: Progress
“It’s times like these we really need to roll up our
sleeves, rally together and find ourselves a scapegoat.”

## Slide 14: Timeline
Chart: Number of Travelers Monitored for Ebola By Month Added
| Oct | Nov | Dec | Jan | Feb | Mar | Apr | 2014 | 2015
Total | 30 | 93 | 108 | 82 | 66 | 133 | 92
Mar 2105
Mar 2104
Apr 2104
May 2104
Jun 2104
Jul 2104
Aug 2104
Sep 2104
Oct 2104
Nov 2104
Dec 2104
Jan 2105
Feb 2105
ELC Leadership Meeting
Project Kick-off Meeting
Houston Meeting
Midland Meeting
San Antonio Meeting
Arlington Meeting
Sub-committee Kick-off Meeting
First Ebola Patient Confirmed
Flight 1143 Manifest Distribute
Flight 1142 Manifest Distributed
Traveler Monitoring Initiated
Second HCW Ebola Case Confirmed

## Slide 15: Ebola
– Tsunami of work
+ Networking and surge capacity exercise
“Because, you see, the kind of work that went into organizing all those daunting, tedious logistical tasks did not just take care of those tasks, they also created the kind of organization that could think together collectively and make hard decisions together, create consensus and innovate, and maybe even more crucially, keep going together through differences.”
  Zeynep Tufekci – Ted Talk – Online social change: easy to organize, hard to win. Zeynep Tufekci is an assistant professor at the School of Information and Library Science at the University of North Carolina, Chapel Hill, and a faculty associate at Harvard's Berkman Center.

## Slide 16: Draft Status
Work in progress
Structure established
  Section and content plan
Sections in different stages
  Drafts with several rounds of review
  First drafts
  Outlines with some details filled in
Work needed to mesh into whole
  Gaps
  Redundancy
  Inconsistency
  Inaccuracy

## Slide 17: Outline
Purpose and Scope
Overview and Assumptions
Concept of Operations
Information Sharing
Routine Disease Surveillance
Outbreak Investigations
Laboratory
Surge Capacity
Appendix

## Slide 18: Highlights
Purpose and Scope –
The overarching goals of this guide are to: 1) capture standards for infectious disease epidemiology in the state, 2) improve communications, and 3) unify epidemiologists during multi-jurisdictional responses.
Roles of local, regional, and state level health departments for investigation of infectious diseases

## Slide 19: Highlights
Information Sharing –
Regional organization is nexus
  Recommendation – Formation of a Regional Epidemiology Workgroup (REW) for ongoing coordination and Regional Epidemiology Coordination Group (REC) for outbreaks and events
Communications directed primarily to adjacent level
Regions serve as liaison between state and local health departments and communications should be directed through them or include them
The state serves as the liaison with CDC and federal partners

## Slide 20: Highlights
Routine Disease Surveillance –
Local health departments are responsible for working with local reporting entities.
Regional health departments serve as the LHD for counties that are not covered by a local health department for disease investigation and provide coordination and training for local health departments in their region.
IDCU coordinates state-wide surveillance to assure standards in case criteria, public health response, reporting, and data quality.

## Slide 21: Highlights
Outbreak Investigations –
Outbreaks are detected by numerous passive or active methods
Affected jurisdictions coordinate efforts to confirm, investigate, and mitigate outbreaks
Regular communication and real time sharing of data and information are needed
Jurisdictional responsibility for investigating a case usually depends on patient’s residence but for some types of outbreaks may be based on the location of the outbreak

## Slide 22: Highlights
Laboratory –
Laboratory testing is needed for diagnosis of cases and recognition or confirmation of outbreak agents
Jurisdictions need to coordinate specimen collection and shipment
Tests at LRN labs should be coordinated by epi staff
  DSHS Laboratory testing should be coordinated through IDCU epis

## Slide 23: Highlights
Surge Capacity –
Epidemiological surge capacity is a jurisdiction’s capability to maintain staffing capacity to manage routine epidemiological investigation systems and support surge epidemiological investigations in response to public health events.
Internal and external resources should be identified
Assistance may be needed for outbreaks and other incidents or to cover temporary staffing gaps
Administrative barriers for accessing assistance and providing it to others should be addressed

## Slide 24: Continue to Develop Document
Sign up to be on the distribution list
  Check “All” or sections of interest
  Or - Text message to 512-969-0433
  Or - Email to laura.tabony@dshs.state.tx.us
Drafts will be distributed for review
Read drafts and contribute to content

## Slide 25: What Next?
Read it
Identify
  Gaps
  Redundancy
  Inconsistency
  Inaccuracy
Discuss it with colleagues
Submit edits and comments

## Slide 26: Workgroup Committees
Project Co-chairs |  | 
Stacy Davlin |  | Region 8
Diana Martinez |  | Harris County PHES
Laura Tabony |  | DSHS State Office
Project Intern |  | 
Blaine Mallon |  | University of Texas SPH
Information Sharing Sub-committee |  | 
Diana Cervantes** |  | Region 2/3
Dusty Gonzalez** |  | Northeast Texas PHD
Huai Lin |  | Region 6/5S
Steven Hinojosa |  | Hidalgo County HHS
Syed Ibrahim |  | Montgomery County Public HD
Donnie Diaz |  | San Antonio Metro HD
Laboratory Sub-committee |  | 
Herminia Alva** |  | Region 11 Harlingen
Hammad Akram** |  | Waco-McLennan County PHD
Kaye Reynolds |  | Fort Bend CO HD (HHS)
Sherry Jin |  | Harris County PHES
Brandy Tiwell |  | DSHS State Office
Outbreak Investigations Sub-committee |  | 
Rebecca Lopez** |  | Region 11
Brenda Thorne** |  | City of Houston HHS Dept
Virginia Headley |  | Williamson County and Cities HD
Darrell Irvin |  | Beaumont Public HD
Emily Hall |  | Dallas County HHS
Shelly Dilbeck |  | Hardin CO HD
Becky Smith Gates |  | Midland Health and Senior Services
Nicolette Janoski |  | Tarrant County PHD
Routine Disease Surveillance Sub-committee |  | 
Kevin McClaran** |  | Region 1
Bonnie Feldt** |  | Region 7
Darrell Irvin |  | Beaumont Public HD
Lacey Sanders |  | Bell County PHD
Yvonne Vasquez |  | City of El Paso DPH
Juan Rodriguez |  | Denton County HD
Shelly Dilbeck |  | Hardin CO HD
Harold Roquemore |  | Wichita Falls Health District
Surge Capacity Sub-committee |  | 
Winston Jackson** |  | Region 9/10
Brenda Thorne** |  | City of Houston HHSD
Lacey Sanders |  | Bell County PHD
Mary McConnell |  | City of Lubbock HD

## Slide 27: Workgroup Representatives
Brenda Hart, Heidi Threadgill |  | Region 2/3
Vicki Harris |  | Region 4/5N
Avi Raju, David Kolberson, Gerald Damm |  | Region 9/10
Kathy Parker, Miguel Cervantes, Vanessa Palacios, |  | Region 9/10
Wayne Rose |  | Abilene-Taylor CO HD
Christina Orona, Gordon Mattimae, Mary Lou Cornejo |  | Andrews HD
Mary Nichols |  | Angelina CO & Cities Health Dist
Heather Cooks-Sinclair |  | Austin Travis County HHSD
Jan Prejean, Jim Sosa |  | Brazoria CO HD
Cliff Karnes, Roy Jones |  | Brownwood/Brown County HD
Cami Smith |  | Chambers CO HD
Rhonda, Simon |  | Cherokee CO HD
Casie Stoughton, Meghan Griffin, Stephanie Sanchez, |  | City of Amarillo DPH
Jorge Gallegos |  | City of El Paso DPH
Marcia Wolverton |  | City of Houston HHSD
Keila Castillo |  | City of Laredo HD
Beckie Brawley |  | City of Lubbock HD
Jawaid Asghar |  | Collin CO Health Care Services
Gwen Mills, Kenda Deputy |  | Comal County HD
Linda Simmons |  | Corpus Christi-Nueces Co PHD
Emily Carroll |  | Corsicana-Navarro PHealth Dist
Amanda Robison-Chadwell |  | Ector County HD
Randy Valcin |  | Galveston CO Health Dist
Don Hart, Joy Pierson, Vikki Yeatts |  | Garland City HD
Amanda Ortiz, Denise Wardell, Randy Brooks, |  | Grayson CO HD
Debby Maddox, Pam Andrews |  | Greenville-Hunt CO HD
Monty Gomez |  | Hays County HD
Donna Reeves |  | Jasper-Newton CO PHealth Dist
Jennifer Dugosh, Wendy Cole |  | Live Oak County HD
Crystal Piña, Esther Lopez, Jeanette Vosquez |  | Medina County HD
Michelle Garcia, Pam Muennink |  | Medina County HD
Diane Leftwich |  | Milam County HD
Jack McCasland |  | Plainview-Hale County HD
Martha Simien |  | Port Arthur
Lorina Rodriguez, Marie Aguilar |  | San Angelo HD
Katrina Reynolds |  | Scurry CO Health Unit
Amber Carlisle, Soronya Shafer, Zach Holbrooks |  | South Plains PHD
Sheila Ellison |  | Sweetwater-Nolan CO HD
Delilah Perez |  | Victoria County HD

## Slide 28: Help Wanted
“Miss Roth, send someone in here to roll up our sleeves.”