## Title
Document Details
Title | Grant Project Project Pipeline
Version | 1
Fiscal Year
Leadership Directory
Director I
Director II
Director III
Directior IV
Communication Director
Any other relevant leadership to include
Strategic Planning Team
Director I
Director II
Director III
Project Manager
Project Manager

## Legend
Column Name | Description of Information
Row | Used for reference in discussions.
Project Name | The name of the project that the item corresponds to. Multiple documents or tasks may be associated with the same project. If document progress is dependent on the completion of a different document, the order of documents within a project will be listed in the order in which they must be completed.
Item Name | The name of the document or tasks that is being tracked in the row.
Description of Document | Brief description of the project to reference its purpose, function, and who should be involved in the development/implementation of the document or task.
Project Manager | The project manager assigned to track the progress and completion of the document/project.
Owner | The individual responsible efforts in completing the document/project.
Rank | Priority level for a document/project (Low, Medium, or High)
Start Date | Date resources or efforts should begin
Planned End Date | Date resources or efforts is anticipated to end
Actual End Date | Date resources or efforts were concluded
Status | Indicating the health of the project/document. C - Complete - Project is 100% Complete G - Green - Is meeting objectives and is on schedule Y - Yellow - Concerns exist over meeting objectives / deliverables or the planned schedule R - Red - Project will not meet objectives or schedule (planned or required) H - Hold - Project or Intake has been placed on Hold N - No Status - Project is not within OPHP roadmap capacity and has no current status X - Cancelled - Project has been "cancelled" or "closed" as opposed to having been completed.
Red, Blue, and Gray Lines
Items Below the Gray Line | These are active items currently in Progress.
Items Below the Red Line | These are items not currently in Progress due to capacity limits. This may mean time, resources, or priority.
Items Below the Blue Line | These are items not currently in progress with a future start date.
Items Below the Purple Line | These items have been completed but require additional monitoring by to project management team.

## Ref-Risk Definitions
This is used for reference only when considering status of project
Severity / Impact or Criticality Rating
RED - Critical Impact, i.e. would:
- Impact critical project objectives
- Critical disruption to ongoing business
- Critical/unacceptable cost/time or performance impact
- Critical impact on other projects
AMBER / YELLOW - Significant Impact, i.e. :
- Impact significant business objectives
- Significant disruption to ongoing business
- Significant/unacceptable cost/time or performance impact
- Significant impact on other projects
GREEN - Minor Impact, i.e. :
- Impact minor business objectives
- Minor disruption to ongoing business
- Minor/acceptable cost/time or performance impact.

## Pipeline
| Project |  |  |  |  | Priority |  | Project Schedule |  |  | Project Status
Row | Project Name | Item Name | Description | Project Manager | Owner | Rank | Start Date | Planned End Date | Actual End Date | Status | Pending Issues / Comments
Active Projects
1 | Monthly Reports | Narrative Report Template | Development of a template for grant contractors to report qualitative information and community feedback. |  |  | L | 2022-05-09 | 2022-08-31 |  | G | 5/9: Project kickoff meeting. Brainstormed questions to include and assigned action items. Next meeting to regroup on 5/13.
Projects On Hold
1
Projects coming up
1
Projects monitoring
1 | Ex: Grant Partner Work Plan Template | Grant Partner Work Plan Template | Create a template to provide to grant partners needing a more detailed and/or updated work plan. The template will outline the level of detail needed. |  |  | M | 2022-04-29 | 2022-05-20 | 2022-07-01 | C | Project completed on 7/1. Monitoring until the work plan template is introduced to the grant partners.
Note on A2: Row Used for reference in discussions.
Note on B2: Project Name The formal name of the project which should be used consistently in all documentation.
Note on E2: Project Manager The individual identified as the project manager.
Note on F2: Size Project classification as either Small, Medium, Large, or XL based on the Information Technology Project Classification Method. A project classified as XL is a Major Information Resource Project (MIRP) as specified in Texas Government Code, Section 2054.003(12).
Note on G2: Rank The Ranking of this project: H - High, Must Have M - Medium, Significant L - Low NP - Not Prioritized Until the "IT agency wide" approach is agreed, each group should use their methodology for ranking projects
Note on H2: Start Date For projects below the red line, this is the date the intake was received in Governance. For projects above the red line, this is the planned start date of the project.
Note on I2: End Date Enter planned or required end date for the project.
Note on K2: Project Status C - Complete - Project is 100% Complete G - Green - Is meeting objectives and is on schedule Y - Yellow - Concerns exist over meeting objectives / deliverables or the planned schedule R - Red - Project will not meet objectives or schedule (planned or required) H - Hold - Project or Intake has been placed on Hold N - No Status - Project is not within ISS roadmap capacity and has no current status X - Cancelled - Project has been "cancelled" or "closed" as opposed to having been completed.
Note on L2: Pending Issues / Comments For any project with a status of either Yellow or Red, provide a brief statement as to the reason. Also, should be prepared to discuss mitigation to bring project back on track
Items Below the Red Line: Projects or Intakes that are not currently in Progress due to capacity limits. This may mean time, resources or funding.
Items Below the Blue Line: Intakes that remain in IT Solutioning Phase. They have not been presented to the Requestor, Mgmt Comm or ESC for review or approval. The Start Date reflects the date the Intake was submitted to Governance with Management Committee Chair approval.
Items Below the Gray Line: These items are included for awareness only. IT has not received an Official request (Ex: Intake form) with the high level requirements documented. IT is not working on providing a solution for these items.

## Completed
| Project | [5 empty] | Priority | Project Schedule |  |  | Project Status
Row | Project Name | Item Name | Description of Document | Project Manager | Owner | Comms Involved | Rank | Start Date | Planned End Date | Actual End Date | Status | Closing Comments
1 | Ex: Meetings | Talking Points for county judge meetings | A document that guides staff on how to discuss the Grant Projects with stakeholders | Joey | Team Member (should not be a project manager) |  | H | mm/dd/yyyy | mm/dd/yyyy | mm/dd/yyyy | C | This column is used for comments that track progress throughout the project. Closing comments should be included on this page: details about how the project was completed/launched, and a link to where the document is saved in SharePoint (if applicable).
2
3
4
5
6
7
8
9
Note on A2: Row Used for reference in discussions.
Note on B2: Project Name The formal name of the project which should be used consistently in all documentation.
Note on E2: Project Manager The individual identified as the project manager.
Note on F2: Size Project classification as either Small, Medium, Large, or XL based on the Information Technology Project Classification Method. A project classified as XL is a Major Information Resource Project (MIRP) as specified in Texas Government Code, Section 2054.003(12).
Note on H2: Rank The Ranking of this project: H - High, Must Have M - Medium, Significant L - Low NP - Not Prioritized Until the "IT agency wide" approach is agreed, each group should use their methodology for ranking projects
Note on I2: Start Date For projects below the red line, this is the date the intake was received in Governance. For projects above the red line, this is the planned start date of the project.
Note on J2: End Date Enter planned or required end date for the project.
Note on L2: Project Status C - Complete - Project is 100% Complete G - Green - Is meeting objectives and is on schedule Y - Yellow - Concerns exist over meeting objectives / deliverables or the planned schedule R - Red - Project will not meet objectives or schedule (planned or required) H - Hold - Project or Intake has been placed on Hold N - No Status - Project is not within ISS roadmap capacity and has no current status X - Cancelled - Project has been "cancelled" or "closed" as opposed to having been completed.
Note on M2: Pending Issues / Comments For any project with a status of either Yellow or Red, provide a brief statement as to the reason. Also, should be prepared to discuss mitigation to bring project back on track
Items Below the Red Line: Projects or Intakes that are not currently in Progress due to capacity limits. This may mean time, resources or funding.
Items Below the Blue Line: Intakes that remain in IT Solutioning Phase. They have not been presented to the Requestor, Mgmt Comm or ESC for review or approval. The Start Date reflects the date the Intake was submitted to Governance with Management Committee Chair approval.
Items Below the Gray Line: These items are included for awareness only. IT has not received an Official request (Ex: Intake form) with the high level requirements documented. IT is not working on providing a solution for these items.