## Sheet1
2019 GOALS | 2019 OBJECTIVES | 2019 RELATED QUALITY ACTIVITIES | TIMELINE | LEAD | DONE
1. Increase retention in care to an average of 75% across the BFACC network. | Establishing baseline measuements using AIRS and new reporting forms | Quarterly data extraction from all consortium sites | Quarterly | Hager
|  | Quarterly review of data with QM Work Group and QM Committee | Quarterly | Hager
|  | Quarterly data discussions with each consortium site | Quarterly | Hager
|  | Implementation of revised data entry tools for QI performance | Ongoing | Site Staff
|  | Setting bottom threshold for low performance and special TA | December, 2019 | Hager
|  | Special TA provided to groups not meeting bottom threshold | March, 2020 | Hager
|  | Evaluation of revised QM performance processes | September, 2019 | Hager | August, 2019
2. Increase viral load suppression to an average of 85% across the BFACC network. | Establishing baseline measuements using AIRS and new reporting forms | Quarterly data extraction from all consortium sites | Quarterly | Hager
|  | Quarterly review of data with QM Work Group and QM Committee | Quarterly | Hager
|  | Quarterly data discussions with each consortium site | Quarterly | Hager
|  | Implementation of revised data entry tools for QI performance | Ongoing | Site Staff
|  | Setting bottom threshold for low performance and special TA | December, 2019 | Hager
|  | Special TA provided to groups not meeting bottom threshold | March, 2020 | Hager
|  | Evaluation of revised QM performance processes | September, 2019 | Hager | August, 2019
3. Establish Consortium-Wide QI Project | Creation of process and system to analyze quality data for QI Project planning | Implement new QM performance system for BFACC | June, 2019 | Hager | June, 2019
|  | Implement new QM committee and work group structure | June, 2019 | Hager | June, 2019
|  | Develop and implement standard process to review BFACC data | June, 2019 | Hager | June, 2019
|  | Set BFACC member expectations around CQM and QI | June, 2019 | Hager | June, 2019
| Selection and implementation of QI Project | Provide detailed presentations on available perforamnce data | June, 2019 | Hager | June, 2019
|  | Add 1 consumer to the QM Work Group | December, 2019 | Site Staff
|  | Add 1 consumer to the CQM Committee | December, 2019 | Site Staff
|  | Traingulation of a consortium QI project target and aim | December, 2019 | Site Staff
|  | Implementation of member QI projects using standard tools | December, 2019 | Site Staff
4. Development of routine staff and patient experience evaluation | Needs Assessment of staff to calibrate evaluation method | Create needs assessment tool with BFACC staff input | December, 2019 | Hager
|  | Deployment of needs assessment | February, 2020 | Site Staff
|  | Evaluation and executive summary of the needs assessment | April, 2020 | Hager
| Development of appraoch to experience evaluation | Generate menu of options to select in a survey and deploy survey | January, 2020 | Hager
|  | Provide candid responses related to experience evaluation | January, 2020 | Site Staff
|  | Provided input on the development of new and revised tools | January, 2020 | Site Staff
| Deployment of approach to experience evaluation | Pilot revised patient experience tools | February, 2020 | Site Staff
|  | Pilot new staff experience evaluation tools | April, 2020 | Site Staff
|  | QM Plan updated to include new experience evaluation activities | June, 2020 | Hager