## Sheet1
20xx-20xx Texas School Health Advisory Committee Work Plan
Updated: 2020-2021
| Components/Tasks |  | Scheduled | Scheduled | Who | Status* | Notes
|  | Goal | Start | End
|  | A, B, or C | (Use strikethrough to show revisions.)
*Status Options: Not Started, On Target, At Risk, Delayed, Complete
Objective I | IDENTIFY, INTERESTS AND RESOURCES | A, B, C
| 1. Develop recomendations for diet sodas in schools to send to the TDA as requested. |  |  | 2020-03-03 | SHAC Members | Complete | Recommendations to TDA and posted to website. Revisions for update in progress 5-14-20.
| 2. Develop resources for mental health and school connectedness. |  |  | 2020-11-12 | Mental Health Sub-Committee | Complete | Now on the website.
| 3. Investigate bus idling and develop a statement on this issue. |  |  | 2020-03-03 | SHAC Members | Complete | Article posted in TASB magazine. Revised for updates on May 9, 2020 and posted to website.
| 4. Investigate possible tools for the development of a parent Guide to FITNESSGRAM® and development of a Parent Notification letter to assist schools with FITNESSGRAM® follow up. |  |  | 2020-11-17 | SHAC Members | Complete | On the website and promoted in the Friday Beat. Revision on hold due to changes in statute.
| 5. Identify best practices in CSH program implementation and make available throughout the state with a focus on rural areas, utilizing the DSHS and TEA websites. Encourage the use of award-winning school programs, such as Fitnessgram, as best practices for student wellness; and, health/fitness interventions identified by Fitnessgram data. |  | 2021-01-09 |  | SHAC Members | On Target | Best practice criteria and application developed.
| 6. Expand the scope of CSH from the four required program components to all eight components of the CSH model and provide education on the eight components of CSH through district school health advisory councils. Research effectiveness of CSH that demonstrates improved academic performance and include in talking points. |  | 2021-03-05 |  | SHAC Members | On Target | Talking points in the development stage. Will forward to DSHS council as recommendation.
Objective II | FACILITATE INTERAGENCY COORDINATION | A, B, C
| 1. Recommend to the DSHS Council that dialogue between the agencies occur on a regular basis with regular, informal attendance at council meetings by at least one pre-appointed member of the TSHAC providing a prepared, authorized report. |  |  | 2021-04-25 | SHAC Members | Complete | Was discussed with Council during annual reporting by chair/vice chair. Members find it difficult to travel to Austin to attend meetings. As of Sept. 2009, council chooses to receive written reports only - no presentation at meetings.
| 2. Distribute agency updates during TSHAC meetings and in the Friday Beat. |  | Ongoing |  | SHAC Members | On Target
| 3. Bring agency surveys and/or results to the TSHAC meeting for updates, input and information sharing. |  | Ongoing |  | Agencies | On Target | DSHS School Nurse Survey, Tobacco survey, YRBS shared with members.
| 4. Share meeting minutes with stakeholders and place on website for public to access. |  | Ongoing |  | Staff | On Target | On website. Up to date
| 5. Call for the Healthy Students-Healthy Families report at each TSHAC meeting. |  | Ongoing |  | TDA | At Risk | TDA committee not active
Objective III | BECOME AND REMAIN CURRENT WITH STATE AND NATIONAL LEGISLATION AND TRENDS | A, B, C
| 1. Continue to exchange timely and accurate information with the Partnership for a Healthy Texas, Texas Action for Healthy Kids, the Alliance for a Healthier Generation, and other ongoing alliances, coalitions and consortiums. |  | Ongoing |  | Partners | On Target | DSHS will collaborate and provide updates to TSHAC membership on all projects.
| 2. Forward CSH modification recommendations to legislators currently working on behalf of CSH. |  |  |  | Each agency to work through internal process. | On Target | From Recommendations for Modifications to CSH Program Requirements. (1.b.)
Objective IV | CONTRIBUTE TIMELY AND APPROPRIATE CONTENT TO DSHS SCHOOL HEALTH WEBSITE | A, B, C
| 1. Contribute timely information for inclusion in the Friday Beat and on website. |  | Ongoing |  | SHAC Members | On Target | Postings of recommendations, presentations, research papers, resources, reports and data
| 2. Place a link to the TSHAC minutes in the Friday Beat once they are appoved and posted. |  | Ongoing |  | Staff | On Target | This has become part of the internal process
| 3. Contribute information regarding the activities that will be added to the DSHS website. |  | Ongoing |  | SHAC Members | On Target | Page established. Posting ongoing.
| 4. Look into establishing a Blog to exchange information among members and stakeholders. |  |  |  | Staff | Delayed | Need to establish objective before we can establish a blog.
| 5. Post best practices to the TSHAC Web site and encourage postings to district SHAC websites. Look into the development of a state level dissemination method to assist local SHACs by providing information on best practices, ideas and support. |  |  |  |  | On Target | Criteria for best practices and application developed 5-14-12. Group will brainstorm dissemination plan.
Objective V | PROVIDE REGIONAL SCHOOL HEALTH SPECIALISTS INFORMATION & RESOURCES FOR STATEWIDE DISTRIBUTION TO LOCAL SHACS | A, B, C
| 1. Build accountability for CSH at the local school district level through the use of an annual progress report to the local school board by the district SHAC. Include longitudinal data in progress report. |  |  | 2020-05-10 | TEA and DSHS | Completed | From Recommendations for Modifications to CSH Program Requirements. (4. and 4.a. ) TSHAC developed template for report.
| 2. Develop an annual evaluation of the implementation process for FITNESSGRAM® testing and data collection methods of school districts to identify best practices. Determine who does data collection. Determine who receives reports. |  |  |  | TEA and DSHS | Not started | From Recommendations for Modifications to CSH Program Requirements. (7.a. and b.) TSHAC will provide guidance.
| 3. Make intervention recommendations based on FITNESSGRAM® data at state, regional and district levels. |  |  |  | SHAC Members | Not started | From Recommendations for Modifications to CSH Program Requirements. (8.a.)
Objective VI | PROMOTE COMMUNICATION AND COLLABORATION AMONG STAKEHOLDERS. | A, B, C
| 1. Continue to update and utilize the Friday Beat as a mechanism to get information to stakeholders. |  | Ongoing |  | SHAC Members | On Target | Friday Beat published weekly.
| 2. Make available a way that stakholders can sign-up for DSHS publications from the DSHS website. |  |  | 2020-03-10 | Staff | Complete | There is a sign up sheet on several pages on the website. School Nurse Notes, TSHAC and Friday Beat.
| 3. Send TSHAC minutes to DSHS Council immediately following each committee meeting. |  | Ongoing |  | Staff | OnTarget
| 4. Direct the TEA to send FITNESSGRAM® reports to the TSHAC, state partners, ESC regional school health specialists and district SHACs. |  |  | 2020-03-10 | TEA | Complete | From Recommendations for Modifications to CSH Program Requirements. (8.c.)
| 5. Recommend the TSHAC review newly mandated programs that fall within the scope of CSH. This would include allowing the TSHAC to provide recommendations on how to fully integrate the new program within existing school curricula. |  |  |  |  | Not Started | Determined at 1-9-2021 TASHAC meeting.
Objective VII | ASSESS AND TRANSLATE CHILD HEALTH RESEARCH DATA INTO CSH PRACTICE ISSUES AND PROVIDE TO STAKEHOLDERS | A, B, C
| 1. Address a specific charge for TSHAC related to SB 530 on CSH programming. A. Assess effectiveness based on Fitnessgram and other research. B. Develop recommendations. |  | 2020-12-01 | 2020-04-01 | TEA and TSHAC members | Complete | Recommendations developed and approved at the April 20, 2021TSHAC meeting. In the process of forwarding to appropriate groups.
| 2. Document FITNESSGRAM® data in a report by appropriate demographic variables such as gender, race, ethnicity, etc. |  |  | 2020-03-10 | TEA | Complete | From Recommendations for Modifications to CSH Program Requirements. (8.e.)
| 3. Develop a list of data resources that is available by agency and organization around the state. |  | 2020-09-08 | 2020-11-15 | SHAC Members | Complete
| 4. Select several data sets to begin looking at during this next year and decide what the next steps will be in utilizing the data that is reviewed. |  | 2020-12-01 |  | SHAC Members | On Target | Data sets document developed November, 2010
| 5. Develop a screening tool to be used by TSHAC for review of proposed school health initiatives. |  |  | 2020-05-10 | SHAC Members | Complete | From Recommendations for Modifications to CSH Program Requirements. (6.a.)